## Sheet1
These tasks do not include: communication with lecturers nor organising meetings amongst ourselves and lecturers. Completion dates and hours per task are estimates only.
Activity | Expected Start Date | Estimate Hours (Per Person) | Actual Start date | Actual Hours spent (Per Person)
Read through of Assignment brief, and discussion relevant to method of approach. | 2019-01-29 | 1 | 2019-01-29 | 1
Create individual accounts and link them to group project (Github repository, Slack) | 2019-01-30 | 1 | 2019-01-30 | 1
Assign responsibilities for separate tasks of project | 2019-01-30 | 1 | 2019-02-12 | 1
Listed all the functional requirements. | 2019-02-12 | 2 | 2019-02-05 | 1
List all attributes. | 2019-02-13 | 1 | 2019-02-05 | 1
Normalise attributes into third normal form, alongside with declaring their table name and their data types. | 2019-02-13 | 5 | 2019-02-06 | 3
Create relevant ERD for normalised data. | 2019-02-15 | 3 | 2019-02-06 | 2
Create user-stories and use-case diagrams | 2019-02-15 | 2 | 2019-02-12 | 3
Finalise sprints for users | 2019-02-18 | 3 | 2019-02-19 | 4
Create SQL scripts to generate all tables in Oracle, alongside with constraints to relevant primary, composite and foreign keys. | 2019-02-21 | 5 | 2019-02-19 | 5
Use SQL Statements to create database tables. | 2019-02-25 | 2 | 2019-02-21 | 2
Design storyboards for front-end view of system (Admin web view, Staff desktop app, Customer mobile app). | 2019-03-06 | 2 | 2019-02-25 | 2
Create front end view for Admin web view, Staff desktop app, and Customer mobile app. | 2019-03-12 | 20 | 2019-03-06 | <
Popularised the database with relevant information.
Design storyboard for front-end view of system (Admin web view, Staff desktop app, Customer mobile app).
Perfect system application(s) interaction with database values (Eg. Fixing logic errors).
Create and finalise Report for project submission.